DETAILED SCHEDULE - NCIL ROUND 4 (August 2026 til August 2027) 

Schedule below is aiming for NCIL funding decisions at the following committees:

· Kingston and North Kingston - June/July 2027 (Date TBC)
· Surbiton - June/July 2027 (Date TBC)

	BID PHASE
	DESCRIPTION
	SCHEDULE/TIMEFRAME FOR CYCLE 4

	PHASE ONE (Part 1) - CALL FOR BIDS AND EXPRESSION OF INTERESTS (EOIs)
	RBK Comms and NHMs engage internal and external stakeholders and point bidders to Neighbourhood Portal (NP) NCIL webpage for further details.
https://www.kingstonletstalk.co.uk/communities-and-neighbourhoods/ncil/

 Interested bidders submit expressions of interest forms (up until the set deadline). 
	15/08/2026 until 31/10/2026 (2.5 months)

	PHASE ONE (Part 2) - EOI CHECKS 
	Deadline for Expressions of interest (EoIs) passes. EoIs collated and checked 
Internal Consultation occurs on any third party EOIs
 If ok to continue, full project bid report templates and guidance sent to bidders (NB: template also available on NCIL page)
	01/11/2026 until 31/12/2026 (2 months)

	PHASE TWO –

PROJECT BID REPORT SUBMISSION
	Time period allocated for Project Managers (PMs) to compile and submit their full Project Bid Reports 
	01/01/2027 until 30/02/2027 (2 months)

	PHASE THREE (Part 1) –

(DRAFT) COMMITTEE REPORT CIRCULATION TO MEMBERS
	Project bid reports collated and checked by NHMS. Financial report provided by Infrastructure Planning and Delivery Manager. Management and Monitoring Report added along with ‘cover sheet’ to create the Draft Committee Report (NCIL ONLY). Report finalised and circulated to Councillors (as CONFIDENTIAL DOCs)
	01/03/2027 until 30/03/2027 (1 months)

	PHASE THREE (Part 2) 

NEIGHBOURHOOD WORKSHOPS
	Neighbourhood Bid Workshops held with Members for each NH area. Feedback/Queries from workshops fed back to PMs where appropriate
	01/04/2027 until 30/04/2027 (1 month)

	PHASE THREE (Part 3) 

NEIGHBOURHOOD WORKSHOP FEEDBACK
	 Time allocated for NH workshop feedback to be processed, reports to be adjusted etc, Finalised Committee Reports sent to Democratic Services for publication. 
	01/05/2027 until 30/05/2027 (1 month)

	PHASE THREE (Part 4)

PROJECT BID DECISIONS
	Committee Meetings held. Councillors ask final questions of bidders and make allocation/funding decisions. 
	01/06/2027 until 15/07/2027 (1.5 months)

	PHASE FOUR - POST DECISION
	[bookmark: _heading=h.gjdgxs]Successful external bidders sign “Neighbourhood Grant Agreement” and funds released. 
[bookmark: _heading=h.1rutsgk7vad9]Internal (Council) bidders drawdown funds at the end of the Financial Year.
	16/07/2027 until 15/08/2027 (1 month)

	PHASE FIVE - MANAGEMENT AND MONITORING 
	Successful bidders report back as per the terms of the “neighbourhood grant agreement.” Progress reported back to Councillors as part of the next bid cycle.
	Post August 2027



Key:
NH = Neighbourhoood
NHMs = Neighbourhood Managers. 
PMs = Project Managers.

